## Timeline PLAN (hidden)
| OVERALL | DAMS / MOMS |  | OFFSPRING | NULLIPS | CONTROL MALES
2024-01-17 | [7 empty] | Aim 1A
2024-01-18 | Order | [6 empty] | Aim 1B
2024-01-19 | [7 empty] | Aim 2A/2B
2024-01-20
2024-01-21
2024-01-22
2024-01-23 | Arrive / Acclimate
2024-01-24 | Acclimate
2024-01-25 | Acclimate
2024-01-26 | Acclimate
2024-01-27 | Acclimate
2024-01-28 | Acclimate / Handle?
2024-01-29 | Acclimate / Handle?
2024-01-30 | Breed
2024-01-31 | Breed
2024-02-01 | Breed
2024-02-02 | Breed
2024-02-03 | Breed
2024-02-04 | Breed
2024-02-05 | Breed
2024-02-06 | Breed
2024-02-07 | GD 0
2024-02-08 | GD 1
2024-02-09 | GD 2
2024-02-10 | GD 3
2024-02-11 | GD 4
2024-02-12 | GD 5
2024-02-13 | GD 6
2024-02-14 | GD 7
2024-02-15 | GD 8
2024-02-16 | GD 9
2024-02-17 | GD 10
2024-02-18 | GD 11
2024-02-19 | GD 12
2024-02-20 | GD 13
2024-02-21 | GD 14
2024-02-22 | GD 15
2024-02-23 | GD 16
2024-02-24 | GD 17
2024-02-25 | GD 18
2024-02-26 | GD 19
2024-02-27 | GD 20
2024-02-28 | GD 21 | SAC |  |  | SAC? | SAC? | Aim 1A
2024-02-29 | PD 0
2024-03-01 | PD 1
2024-03-02 | PD 2 | Mat obs | CORT / OIL
2024-03-03 | PD 3 | Mat obs | CORT / OIL
2024-03-04 | PD 4 | Mat obs | CORT / OIL
2024-03-05 | PD 5 | Mat obs | CORT / OIL
2024-03-06 | PD 6 | Mat obs | CORT / OIL
2024-03-07 | PD 7 | Mat obs | CORT / OIL |  |  |  | Aim 1A | Aim 1B
2024-03-08 | PD 8 | Mat obs | CORT / OIL
2024-03-09 | PD 9 |  | CORT / OIL
2024-03-10 | PD 10 |  | CORT / OIL
2024-03-11 | PD 11 |  | CORT / OIL
2024-03-12 | PD 12 |  | CORT / OIL
2024-03-13 | PD 13 |  | CORT / OIL
2024-03-14 | PD 14 |  | CORT / OIL
2024-03-15 | PD 15 |  | CORT / OIL
2024-03-16 | PD 16 |  | CORT / OIL
2024-03-17 | PD 17 |  | CORT / OIL
2024-03-18 | PD 18 |  | CORT / OIL
2024-03-19 | PD 19 |  | CORT / OIL
2024-03-20 | PD 20 |  | CORT / OIL
2024-03-21 | PD 21 |  | CORT / OIL
2024-03-22 | PD 22 |  | CORT / OIL
2024-03-23 | PD 23 | BIG SAC | CORT / OIL | EPM | BIG SAC |  | Aim 1A | Aim 1B
2024-03-24 | PD 24 |  |  | FST 1
2024-03-25 | PD 25 |  |  | FST 2 - SAC |  |  | Aim 2A/2B
2024-03-26 | PD 26
2024-03-27 | PD 27
2024-03-28 | PD 28
2024-03-29 | PD 29
2024-03-30 | PD 30
2024-03-31 | PD 31
2024-04-01 | PD 32
2024-04-02 | PD 33
2024-04-03 | PD 34
2024-04-04 | PD 35
2024-04-05 | PD 36
2024-04-06 | PD 37
2024-04-07 | PD 38
2024-04-08 | PD 39
2024-04-09 | PD 40
2024-04-10 | PD 41 |  |  | Sucrose Preference 1
2024-04-11 | PD 42 |  |  | Sucrose Preference 2
2024-04-12 | PD 43 |  |  | Sucrose Preference 3
2024-04-13 | PD 44 |  |  | Sucrose Preference 4
2024-04-14 | PD 45 |  |  | Sucrose Preference 5 + EPM
2024-04-15 | PD 46 |  |  | FST 1
2024-04-16 | PD 47 |  |  | FST 2 - SAC

## Timeline Version 2 (hidden)
| DAMS / MOMS |  |  | OFFSPRING | NULLIPS | CONTROL MALES | BREEDING MALES diff arrivals
2024-01-17 | Fist 20 females | 8 females |  |  |  |  | 10 males | 4 males
2024-01-18 |  | (All aim 1A)
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23 | Acclimate
2024-01-24 | Acclimate
2024-01-25 | Acclimate
2024-01-26 | Acclimate
2024-01-27 | Acclimate
2024-01-28 | Acclimate
2024-01-29 | Acclimate
2024-01-30 | Handle
2024-01-31 | Handle
2024-02-01 | Handle
2024-02-02 | Handle
2024-02-03 | Handle/Breed
2024-02-04 | Breed
2024-02-05 | Breed
2024-02-06 | Breed | Acclimate
2024-02-07 | Breed | Acclimate
2024-02-08 | Breed | Acclimate
2024-02-09 | Breed | Acclimate
2024-02-10 | Breed | Acclimate
2024-02-11 | GD1 | Acclimate
2024-02-12 | GD2 | Acclimate
2024-02-13 | GD3 | Handle/Breed
2024-02-14 | GD4 | Breed
2024-02-15 | GD5 | Breed
2024-02-16 | GD6 | Breed
2024-02-17 | GD7 | Breed
2024-02-18 | GD8 | Breed
2024-02-19 | GD9 | Breed
2024-02-20 | GD10 | Breed
2024-02-21 | GD11 | GD1
2024-02-22 | GD12 | GD2
2024-02-23 | GD13 | GD3
2024-02-24 | GD14 | GD4
2024-02-25 | GD15 | GD5
2024-02-26 | GD16 | GD6
2024-02-27 | GD17 | GD7
2024-02-28 | GD18 | GD8
2024-02-29 | GD19 | GD9
2024-03-01 | GD20 | GD10
2024-03-02 | GD21 | GD11
2024-03-03 | GD22 | GD12
2024-03-04 | GD23 | GD13
2024-03-05 | PD1 | GD14
2024-03-06 | PD2 | GD15 | CORT / OIL
2024-03-07 | PD3 | GD16 | CORT / OIL
2024-03-08 | PD4 | GD17 | CORT / OIL
2024-03-09 | PD5 | GD18 | CORT / OIL
2024-03-10 | PD6 | GD19 | CORT / OIL
2024-03-11 | PD7 | GD20 | CORT / OIL
2024-03-12 | PD8 | GD21 | CORT / OIL
2024-03-13 | PD9 | GD22 | CORT / OIL
2024-03-14 | PD10 | GD23 | CORT / OIL
2024-03-15 | PD11 | PD1 | CORT / OIL
2024-03-16 | PD12 | PD2 | CORT / OIL
2024-03-17 | PD13 | PD3 | CORT / OIL
2024-03-18 | PD14 | PD4 | CORT / OIL
2024-03-19 | PD15 | PD5 | CORT / OIL
2024-03-20 | PD16 | PD6 | CORT / OIL
2024-03-21 | PD17 | PD7 | CORT / OIL
2024-03-22 | PD18 | PD8 | CORT / OIL
2024-03-23 | PD19 | PD9 | CORT / OIL
2024-03-24 | PD20 | PD10 | CORT / OIL
2024-03-25 | PD21 | PD11 | CORT / OIL
2024-03-26 | PD22 | PD12 | CORT / OIL
2024-03-27 | PD23 | PD13 | CORT / OIL |  | SAC? | SAC?
2024-03-28 | PD24 | PD14
2024-03-29 | PD25 | PD15 |  | SAC
2024-03-30 | PD26 | PD16
2024-03-31 | PD27 | PD17
2024-04-01 | PD28 | PD18
2024-04-02 | PD29 | PD19
2024-04-03 | PD30 | PD20
2024-04-04 | PD31 | PD21
2024-04-05 | PD32 | PD22
2024-04-06 | PD33 | PD23
2024-04-07 | PD34
2024-04-08 | PD35
2024-04-09 | PD36
2024-04-10 | PD37
2024-04-11 | PD38
2024-04-12 | PD39
2024-04-13 | PD40
2024-04-14 | PD41
2024-04-15 | PD42
2024-04-16 | PD43
2024-04-17 | PD44
2024-04-18 | PD45 |  |  | EPM
2024-04-19 | PD46 |  |  | FST 1
2024-04-20 | PD47 |  |  | FST2/SAC
2024-04-21
2024-04-22
2024-04-23
2024-04-24
2024-04-25
2024-04-26
2024-04-27
2024-04-28
2024-04-29
2024-04-30

## Dam IDs
Animal ID | Tile ids | Sex | GD0 | GD21 | PD0 | Parity | Sac Day (GD20, PD8, PD23) | Treatment (CORT/OIL/NONE) | Group | SAC DATE | Perfusion time | Notes
B40 | B0123_007 | Female dam | 2024-02-15 | 2024-03-13 | 2024-03-08 | Nulliparous | PD23 | NONE | Nullip-PD23-NONE | 2024-03-31 | Perfusion: 12:17-12:22
B41 | B0126_007 | Female dam | 2024-02-04 | 2024-02-25 | 2024-02-25 | Nulliparous | PD8 | NONE | Nullip-PD8-NONE | 2024-03-04 | Perfusion: 12:53-12:56
B42 | B0119_002 | Female dam | 2024-02-05 | 2024-02-26 | 2024-02-25 | Nulliparous | PD8 | NONE | Nullip-PD8-NONE | 2024-03-04 | Perfusion: 1:06-1:09
B21 | B0122_002 | Female dam | 2024-03-03 | 2024-03-24 | 2024-03-24 | Pregnant | GD20 | NONE | Preg-GD20-NONE | 2024-03-23 | Perfusion: 12:48-12:52
B27 | B0124_014 | Female dam | 2024-03-08 | 2024-03-25 | 2024-03-25 | Pregnant | GD20 | NONE | Preg-GD20-NONE | 2024-03-28 | Perfusion: 12:57-1:00
B20 | B0124_013 | Female dam | 2024-03-08 | 2024-03-29 | 2024-03-29 | Pregnant | GD20 | NONE | Preg-GD20-NONE | 2024-03-28 | Perfusion: 12:38-12:42
B01 | B0119_003 | Female dam | 2024-02-29 | 2024-03-21 | 2024-03-21 | Pregnant | PD8 | NONE | Preg-PD8-NONE | 2024-03-29 | Perfusion: 12:43-12:51 | Longer perfusion
B31 | B0126_008 | Female dam | 2024-02-21 | 2024-03-13 | 2024-03-14 | Pregnant | PD8 | NONE | Preg-PD8-NONE | 2024-03-21 | Perfusion: 1:02-1:08
B11 | B0122_007 | Female dam | 2024-02-07 | 2024-02-28 | 2024-02-28 | Pregnant | PD8 | NONE | Preg-PD8-NONE | 2024-03-07 | Perfusion: 1:40-1:46 | Brain is tilted in the mold (froze on an uneven plane of OCT) | Sending both brains so that you can decide which would be best for MerFish
B02 | B0122_008 | Female dam | 2024-02-06 | 2024-02-27 | 2024-02-28 | Pregnant | PD8 | NONE | Preg-PD8-NONE | 2024-03-06 | Perfusion: 1:24-1:29 | Slight sign of blood vessels, not a perfect perfusion
B18 | B0117_004 | Female dam | 2024-02-04 | 2024-02-25 | 2024-02-25 | Pregnant | PD8 | OIL | Preg-PD8-OIL | 2024-03-04 | Perfusion: 1:26-130
B24 | B0123_009 | Female dam | 2024-02-21 | 2024-03-13 | 2024-03-13 | Pregnant | PD8 | OIL | Preg-PD8-OIL | 2024-03-21 | Perfusion: 11:41-11:45
B37 | B0126_009 | Female dam | 2024-02-21 | 2024-03-13 | 2024-03-14 | Pregnant | PD8 | OIL | Preg-PD8-OIL | 2024-03-21 | Perfusion: 11:52-11:56 | Slight cortex damage- posterior right hemisphere
B19 | B0119_004 | Female dam | 2024-02-04 | 2024-02-25 | 2024-02-25 | Pregnant | PD8 | CORT | Preg-PD8-CORT | 2024-03-04 | Perfusion: 1:41-1:45
B32 | B0126_006 | Female dam | 2024-02-21 | 2024-03-13 | 2024-03-13 | Pregnant | PD8 | CORT | Preg-PD8-CORT | 2024-03-21 | Perfusion: 1:20-1:25
B33 | B0123_014 | Female dam | 2024-02-28 | 2024-03-20 | 2024-03-20 | Pregnant | PD8 | CORT | Preg-PD8-CORT | 2024-03-28 | Perfusion: 12:08-12:12
B13 | B0123_006 | Female dam | 2024-02-04 | 2024-02-25 | 2024-02-26 | Pregnant | PD23 | OIL | Preg-PD23-OIL | 2024-03-19 | Perfusion: 12:05-12:10
B06 | B0123_013 | Female dam | 2024-02-06 | 2024-02-27 | 2024-02-28 | Pregnant | PD23 | OIL | Preg-PD23-OIL | 2024-03-21 | Perfusion: 12:02-12:10
B28 | B0123_010 | Female dam | 2024-02-08 | 2024-02-29 | 2024-02-29 | Pregnant | PD23 | OIL | Preg-PD23-OIL | 2024-03-23 | Perfusion: 12:17-12:21
B15 | B0123_008 | Female dam | 2024-02-04 | 2024-02-25 | 2024-02-26 | Pregnant | PD23 | CORT | Preg-PD23-CORT | 2024-03-20 | Perfusion: 12:18-12:23
B26 | B0124_015 | Female dam | 2024-02-07 | 2024-02-28 | 2024-02-29 | Pregnant | PD23 | CORT | Preg-PD23-CORT | 2024-03-22 | Perfusion: 11:54-11:58
B08 | B0124_012 | Female dam | 2024-02-16 | 2024-03-08 | 2024-03-09 | Pregnant | PD23 | CORT | Preg-PD23-CORT | 2024-03-31 | Perfusion: 12:47-12:51

## Tile ids
B01 | B0119_003
B02 | B0122_008
B03 | B0130_004
B06 | B0123_013
B08 | B0124_012
B11 | B0122_007
B13 | B0123_006
B14 | B0130_006
B15 | B0123_008
B18 | B0117_004
B19 | B0119_004
B20 | B0124_013
B21 | B0122_002
B23 | B0126_010
B24 | B0123_009
B26 | B0124_015
B27 | B0124_014
B28 | B0123_010
B31 | B0126_008
B32 | B0126_006
B33 | B0123_014
B37 | B0126_009
B40 | B0123_007
B41 | B0126_007
B42 | B0119_002
B47 | B0130_008
B48 | B0130_003

## Offspring IDs
Animal ID | Sex | Offspring sex | Sac day | Treatment (CORT/OIL/NONE) | Group | SAC DATE | Perfusion time | Notes
BP73 | Female pup | F-Offspring | PD30 | OIL | F-Offspring-PD30-OIL | 2024-04-07 | 10:53-10:57 |  | Unfortunatly added an extra CORT PD30 group instead of a third PD30 OIL group for pups - so only 2 per gorup for PD30, OIL Male and female pups. Sent the extra CORT group pups.
BP74 | Female pup | F-Offspring | PD30 | OIL | F-Offspring-PD30-OIL | 2024-04-07 | 10:53-10:56 | Not a great perfusion (blood vessels may be visible)
BP75 | Male pup | M-Offspring | PD30 | OIL | M-Offspring-PD30-OIL | 2024-04-07 | 11:09-11:12
BP76 | Male pup | M-Offspring | PD30 | OIL | M-Offspring-PD30-OIL | 2024-04-07 | 11:11-11:15
BP49 | Female pup | F-Offspring | PD30 | CORT | F-Offspring-PD30-CORT | 2024-03-30 | 11:20-11:25
BP50 | Female pup | F-Offspring | PD30 | CORT | F-Offspring-PD30-CORT | 2024-03-30 | 11:20-11:26
BP89 | Female pup | F-Offspring | PD30 | CORT | F-Offspring-PD30-CORT | 2024-04-07 | 11:46-11:49
BP57 | Female pup | F-Offspring | PD30 | CORT | F-Offspring-PD30-CORT | 2024-03-30 | 12:02-12:05 | Extra
BP51 | Male pup | M-Offspring | PD30 | CORT | M-Offspring-PD30-CORT | 2024-03-30 | 11:40-11:44
BP52 | Male pup | M-Offspring | PD30 | CORT | M-Offspring-PD30-CORT | 2024-03-30 | 11:40-11:45
BP91 | Male pup | M-Offspring | PD30 | CORT | M-Offspring-PD30-CORT | 2024-04-07 | 11:47-11:50
BP59 | Male pup | M-Offspring | PD30 | CORT | M-Offspring-PD30-CORT | 2024-03-30 | 12:02-12:06 | Extra-Not a great perfusion (blood vessels may be visible)
BP37 | Female pup | F-Offspring | PD47 | OIL | F-Offspring-PD47-OIL | 2024-04-15 | 12:22-12:25
BP69 | Female pup | F-Offspring | PD47 | OIL | F-Offspring-PD47-OIL | 2024-04-16 | 12:11-12:15
BP70 | Female pup | F-Offspring | PD47 | OIL | F-Offspring-PD47-OIL | 2024-04-16 | 12:11-12:15
BP45 | Female pup | F-Offspring | PD47 | CORT | F-Offspring-PD47-CORT | 2024-04-15 | 11:28-11:32
BP61 | Female pup | F-Offspring | PD47 | CORT | F-Offspring-PD47-CORT | 2024-04-16 | 11:47-11:52
BP62 | Female pup | F-Offspring | PD47 | CORT | F-Offspring-PD47-CORT | 2024-04-16 | 11:46-11:50
BP39 | Male pup | M-Offspring | PD47 | OIL | M-Offspring-PD47-OIL | 2024-04-15 | 12:23-12:29
BP71 | Male pup | M-Offspring | PD47 | OIL | M-Offspring-PD47-OIL | 2024-04-16 | 12:20-12:24
BP72 | Male pup | M-Offspring | PD47 | OIL | M-Offspring-PD47-OIL | 2024-04-16 | 12:22-12:26
BP47 | Male pup | M-Offspring | PD47 | CORT | M-Offspring-PD47-CORT | 2024-04-16 | 11:29-11:32
BP63 | Male pup | M-Offspring | PD47 | CORT | M-Offspring-PD47-CORT | 2024-04-16 | 12:00-12:05
BP64 | Male pup | M-Offspring | PD47 | CORT | M-Offspring-PD47-CORT | 2024-04-16 | 12:00-12:05

## Sac schedule (hidden)
SACS | Date | EST Start time | EST End time | # of Rats | Person 1 | Person 2 | Person 3 | Person 4 (if decap+perf) | Bonnie to substitute if avail
| 2024-03-20 | 11:30 | 1:00 | 5 | Romina | Jennifer | Bonnie | -
| 2024-03-21 | 11:30 | 1:00 | 5 | Romina | Jennifer | Kim | -
| 2024-03-22 | 11:30 | 1:10 | 6 | Romina | Jennifer | Bonnie | -
| 2024-03-23 | 11:30 | 1:00 | 5 | Romina | Jennifer | Kim | -
| 2024-03-24 | 11:30 | 11:40 | 1 | Romina | Someone else? | - | - | GD20 rat
| 2024-03-27 | 11:30 | 2:00 | 8 | Romina | Jennifer | Kim |  | All decap
If only one person needed for this -- Kim can do instead of Jennifer | 2024-03-28 | 11:30 | 11:50 | 2 | Romina | Jennifer | Kim | - | a GD20 rat
| 2024-03-29 | 11:30 | 3:10 | 12 | Romina | Amanda | Kim | - | All decap
| 2024-03-30 | 11:30 | 4:30 | 16 | Romina | Jennifer | Kim | Amanda | 14 decap, 2 perfusions
| 2024-03-31 | 11:30 | 11:40 | 1 | Romina | - | - | -
Bonnie can help | 2024-04-01 | 11:30 | 11:50 | 2 | Romina | Kim, Amanda, Bonnie? | - | N/A
| 2024-04-07 | 11:30 | 3:10 | 12 | Romina | Jennifer | Kim | Amanda | 10 perfusion, 2 decap | need 2 perfusers
No Jennifer; Bonnie can help | 2024-04-13 | 11:30 | 1:50 | 8 | Romina | Amanda | one more maybe | - | All decap
No Jennifer | 2024-04-15 | 11:10 | 2:30 | 12 | Romina | Amanda | Kim |  | 10 perfusion, 2 decap
Start later for Amanda, Jennifer? | 2024-04-16 | 11:30 | 3:10 | 16 | Romina | Jennifer | Kim | Amanda | 10 perfusion, 6 decap | need 2 perfusers
| 2024-04-24 | 11:10 | 3:00 | 12 | Romina | Jennifer | Kim | Bonnie

## Behaviour Schedule (hidden)
Date | Behaviour | Length | # of Rats | Person 1 | Person 2 | EST Start time | EST End time
2024-03-25 | EPM | 5 min per rat | 8 | Paige | lele
2024-03-26 | FST1 | 15 min per rat | 8 | Tallinn | Paige | 9:00 | 9:40
2024-03-27 | FST2 | 5 min per rat | 8 | Kanak
| EPM | 5 min per rat | 12 | Kanak | NA
2024-03-28 | FST1 | 15 min per rat | 12 | Kanak | Lele
| EPM | 5 min per rat | 14 | Kanak | Lele
2024-03-29 | FST1 | 15 min per rat | 14 | Paige
| FST2 | 5 min per rat | 12 | Kanak
2024-03-30 | FST2 | 5 min per rat | 14 | Kanak
2024-04-05 | EPM | 5 min per rat | 2 | Tallinn | NA
2024-04-06 | FST1 | 15 min per rat | 2 | Kanak
2024-04-07 | FST2 | 5 min per rat | 2 | Tallinn
2024-04-11 | EPM | 5 min per rat | 8 | Tallinn | NA
2024-04-12 | FST1 | 15 min per rat | 8 | Paige
2024-04-13 | FST2 | 5 min per rat | 8 | Tallinn
| EPM | 5 min per rat | 10 | Tallinn
2024-04-14 | FST1 | 15 min per rat | 10
| EPM | 5 min per rat | 6
2024-04-15 | FST2 | 5 min per rat | 10
| FST1 | 15 min per rat | 6
2024-04-16 | FST2 | 5 min per rat | 6
2024-04-22 | EPM | 5 min per rat | 12 | Tallinn
2024-04-23 | FST1 | 15 min per rat | 12 | Tallinn
2024-04-24 | FST2 | 5 min per rat | 12 | Tallinn

## Pup allocations (hidden)
CORT+ | [5 empty] | CORT- |  |  |  |  | Culling to 12 not doing this
Dam 1 | Dam 2 | Dam 3 | Dam 4 | Dam 5 |  | Dam 1 | Dam 2 | Dam 3 | Dam 4 | Dam 5
F1 | F1 | F1 | F1 | F1 |  | F1 | F1 | F1 | F1 | F1 |  | PD25
F2 | F2 | F2 | F2 | F2 |  | F2 | F2 | F2 | F2 | F2 |  | PD47
F3 | F3 | F3 | F3 | F3 |  | F3 | F3 | F3 | F3 | F3
F4 | F4 | F4 | F4 | F4 |  | F4 | F4 | F4 | F4 | F4
F5 | F5 | F5 | F5 | F5 |  | F5 | F5 | F5 | F5 | F5
F6 | F6 | F6 | F6 | F6 |  | F6 | F6 | F6 | F6 | F6
M1 | M1 | M1 | M1 | M1 |  | M1 | M1 | M1 | M1 | M1
M2 | M2 | M2 | M2 | M2 |  | M2 | M2 | M2 | M2 | M2
M3 | M3 | M3 | M3 | M3 |  | M3 | M3 | M3 | M3 | M3
M4 | M4 | M4 | M4 | M4 |  | M4 | M4 | M4 | M4 | M4
M5 | M5 | M5 | M5 | M5 |  | M5 | M5 | M5 | M5 | M5
M6 | M6 | M6 | M6 | M6 |  | M6 | M6 | M6 | M6 | M6
CORT+ | [10 empty] | CORT-
Dam 1 | Dam 2 | Dam 3 | Dam 4 | Dam 5 | Dam 6 | Dam 7 | Dam 8 | Dam 9 | Dam 10 |  | Dam 1 | Dam 2 | Dam 3 | Dam 4 | Dam 5 | Dam 6 | Dam 7 | Dam 8 | Dam 9 | Dam 10 | Culling to 10
[11 empty] | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | F1 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | F2 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | F3 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | F4 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | F5 | F5 | F5 | F5 | F5 | F5 | F5 | F5 | F5 | F5 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | M1 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | M2 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | M3 | M3 | M3 | M3 | M3 | M3 | M3 | M3 | M3 | M3 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | M4 | M4 | M4 | M4 | M4 | M4 | M4 | M4 | M4 | M4 | bar: CORT+ Dam 1 to CORT+ Dam 10
[11 empty] | M5 | M5 | M5 | M5 | M5 | M5 | M5 | M5 | M5 | M5 | bar: CORT+ Dam 1 to CORT+ Dam 10

## Timeline ACTUAL (hidden)
|  |  | DAMS / MOMS | [10 empty] | OFFSPRING | [10 empty] | NULLIPS | CONTROL MALES | BREEDING MALES diff arrivals
|  |  | Group 1 (n=6) | Group 2 (n=3) | Group 3 (n=3) | Group 4 (n=6) | Group 5 (n=6) | Group 6 (n=1) | Group 7 (n=2) | Group 8 n=5 | Group 9 n=2 | Group 10 n=1 | Group 11 n=1 | Group 1 (n=30,30) | Group 2 (n=15,15) | Group 3 (n=15,15) | Group 4 (n=30,30) | Group 5 (n=30,30) | Group 6 (n=5,5) | Group 7 (n=10,10) | Group 8 (n=25,25) | Group 9 n=2 | Group 10 n=1 | Group 11 n=1
2024-01-17 | [25 empty] | 10 males | 4 males
2024-01-18
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23 |  |  | 44 females, 10 males arrive
2024-01-24 |  |  | Acclimate
2024-01-25
2024-01-26
2024-01-27
2024-01-28
2024-01-29
2024-01-30 |  |  | Handle
2024-01-31
2024-02-01
2024-02-02
2024-02-03 |  |  | Breed
2024-02-04 |  | Day 0 | GD0
2024-02-05 |  | Day 1 | GD1 | GD0
2024-02-06 |  | Day 2 | GD2 | GD1 | GD0
2024-02-07 |  | Day 3 | GD3 | GD2 | GD1 | GD0
2024-02-08 |  | Day 4 | GD4 | GD3 | GD2 | GD1 | GD0
2024-02-09 |  | Day 5 | GD5 | GD4 | GD3 | GD2 | GD1 | GD0
2024-02-10 |  | Day 6 | GD6 | GD5 | GD4 | GD3 | GD2 | GD1
2024-02-11 |  | Day 7 | GD7 | GD6 | GD5 | GD4 | GD3 | GD2
2024-02-12 |  | Day 8 | GD8 | GD7 | GD6 | GD5 | GD4 | GD3
2024-02-13 |  | Day 9 | GD9 | GD8 | GD7 | GD6 | GD5 | GD4
2024-02-14 |  | Day 10 | GD10 | GD9 | GD8 | GD7 | GD6 | GD5
2024-02-15 |  | Day 11 | GD11 | GD10 | GD9 | GD8 | GD7 | GD6
2024-02-16 |  | Day 12 | GD12 | GD11 | GD10 | GD9 | GD8 | GD7 | GD0
2024-02-17 |  | Day 13 | GD13 | GD12 | GD11 | GD10 | GD9 | GD8 | GD1
2024-02-18 |  | Day 14 | GD14 | GD13 | GD12 | GD11 | GD10 | GD9 | GD2
2024-02-19 |  | Day 15 | GD15 | GD14 | GD13 | GD12 | GD11 | GD10 | GD3
2024-02-20 |  | Day 16 | GD16 | GD15 | GD14 | GD13 | GD12 | GD11 | GD4
2024-02-21 |  | Day 17 | GD17 | GD16 | GD15 | GD14 | GD13 | GD12 | GD5 | GD0
2024-02-22 |  | Day 18 | GD18 | GD17 | GD16 | GD15 | GD14 | GD13 | GD6 | GD1
2024-02-23 |  | Day 19 | GD19 | GD18 | GD17 | GD16 | GD15 | GD14 | GD7 | GD2
2024-02-24 |  | Day 20 | GD20 | GD19 | GD18 | GD17 | GD16 | GD15 | GD8 | GD3
2024-02-25 |  | Day 21 | GD21 | GD20 | GD19 | GD18 | GD17 | GD16 | GD9 | GD4
2024-02-26 |  | Day 22 | PD 1 | GD21 | GD20 | GD19 | GD18 | GD17 | GD10 | GD5
2024-02-27 |  | Day 23 | PD 2 | PD 1 | GD21 | GD20 | GD19 | GD18 | GD11 | GD6
2024-02-28 |  | Day 24 | PD 3 | PD 2 | PD 1 | GD21 | GD20 | GD19 | GD12 | GD7 | GD0
2024-02-29 |  | Day 25 | PD 4 | PD 3 | PD 2 | PD 1 | GD21 | GD20 | GD13 | GD8 | GD1 | GD0
2024-03-01 |  | Day 26 | PD 5 | PD 4 | PD 3 | PD 2 | PD 1 | GD21 | GD14 | GD9 | GD2 | GD1
2024-03-02 |  | Day 27 | PD 6 | PD 5 | PD 4 | PD 3 | PD 2 | PD 1 | GD15 | GD10 | GD3 | GD2
2024-03-03 |  | Day 28 | PD 7 | PD 6 | PD 5 | PD 4 | PD 3 | PD 2 | GD16 | GD11 | GD4 | GD3 | GD0
2024-03-04 |  | Day 29 | PD 8 | PD 7 | PD 6 | PD 5 | PD 4 | PD 3 | GD17 | GD12 | GD5 | GD4 | GD1
2024-03-05 |  | Day 30 | PD 9 | PD 8 | PD 7 | PD 6 | PD 5 | PD 4 | GD18 | GD13 | GD6 | GD5 | GD2
2024-03-06 | Kim away | Day 31 | PD 10 | PD 9 | PD 8 | PD 7 | PD 6 | PD 5 | GD19 | GD14 | GD7 | GD6 | GD3
2024-03-07 | Kim away | Day 32 | PD 11 | PD 10 | PD 9 | PD 8 | PD 7 | PD 6 | GD20 | GD15 | GD8 | GD7 | GD4
2024-03-08 | Kim away | Day 33 | PD 12 | PD 11 | PD 10 | PD 9 | PD 8 | PD 7 | GD21 | GD16 | GD9 | GD8 | GD5
2024-03-09 | Kim away | Day 34 | PD 13 | PD 12 | PD 11 | PD 10 | PD 9 | PD 8 | PD 1 | GD17 | GD10 | GD9 | GD6
2024-03-10 | Kim away | Day 35 | PD 14 | PD 13 | PD 12 | PD 11 | PD 10 | PD 9 | PD 2 | GD18 | GD11 | GD10 | GD7
2024-03-11 | Kim away | Day 36 | PD 15 | PD 14 | PD 13 | PD 12 | PD 11 | PD 10 | PD 3 | GD19 | GD12 | GD11 | GD8
2024-03-12 | Kim away | Day 37 | PD 16 | PD 15 | PD 14 | PD 13 | PD 12 | PD 11 | PD 4 | GD20 | GD13 | GD12 | GD9
2024-03-13 | Kim away | Day 38 | PD 17 | PD 16 | PD 15 | PD 14 | PD 13 | PD 12 | PD 5 | GD21 | GD14 | GD13 | GD10
2024-03-14 | Kim away | Day 39 | PD 18 | PD 17 | PD 16 | PD 15 | PD 14 | PD 13 | PD 6 | PD 1 | GD15 | GD14 | GD11
2024-03-15 | Kim away | Day 40 | PD 19 | PD 18 | PD 17 | PD 16 | PD 15 | PD 14 | PD 7 | PD 2 | GD16 | GD15 | GD12
2024-03-16 | Kim away | Day 41 | PD 20 | PD 19 | PD 18 | PD 17 | PD 16 | PD 15 | PD 8 | PD 3 | GD17 | GD16 | GD13
2024-03-17 | Kim away | Day 42 | PD 21 | PD 20 | PD 19 | PD 18 | PD 17 | PD 16 | PD 9 | PD 4 | GD18 | GD17 | GD14
2024-03-18 | Kim away | Day 43 | PD 22 | PD 21 | PD 20 | PD 19 | PD 18 | PD 17 | PD 10 | PD 5 | GD19 | GD18 | GD15
2024-03-19 | Kim away | Day 44 | PD 23 | PD 22 | PD 21 | PD 20 | PD 19 | PD 18 | PD 11 | PD 6 | GD20 | GD19 | GD16 | PD23
2024-03-20 |  |  |  | PD 23 | PD 22 | PD 21 | PD 20 | PD 19 | PD 12 | PD 7 | GD21 | GD20 | GD17 | PD24 | PD23
2024-03-21 |  |  |  |  | PD 23 | PD 22 | PD 21 | PD 20 | PD 13 | PD 8 | PD 1 | GD21 | GD18 | PD25 | PD24 | PD23
2024-03-22 | [5 empty] | PD 23 | PD 22 | PD 21 | PD 14 | PD 9 | PD 2 | PD 1 | GD19 | PD26 | PD25 | PD24 | PD23
2024-03-23 | [6 empty] | PD 23 | PD 22 | PD 15 | PD 10 | PD 3 | PD 2 | GD20 | PD27 | PD26 | PD25 | PD24 | PD23
2024-03-24 | [7 empty] | PD 23 | PD 16 | PD 11 | PD 4 | PD 3 | GD21 | PD28 | PD27 | PD26 | PD25 | PD24 | PD23
2024-03-25 | [8 empty] | PD 17 | PD 12 | PD 5 | PD 4 | PD 1 | PD29 | PD28 | PD27 | PD26 | PD25 | PD24
2024-03-26 | [8 empty] | PD 18 | PD 13 | PD 6 | PD 5 | PD 2 | PD30 | PD29 | PD28 | PD27 | PD26 | PD25
2024-03-27 | [8 empty] | PD 19 | PD 14 | PD 7 | PD 6 | PD 3 | PD31 | PD30 | PD29 | PD28 | PD27 | PD26
2024-03-28 | [8 empty] | PD 20 | PD 15 | PD 8 | PD 7 | PD 4 | PD32 | PD31 | PD30 | PD29 | PD28 | PD27
2024-03-29 | [8 empty] | PD 21 | PD 16 | PD 9 | PD 8 | PD 5 | PD33 | PD32 | PD31 | PD30 | PD29 | PD28
2024-03-30 | [8 empty] | PD 22 | PD 17 | PD 10 | PD 9 | PD 6 | PD34 | PD33 | PD32 | PD31 | PD30 | PD29
2024-03-31 | [8 empty] | PD 23 | PD 18 | PD 11 | PD 10 | PD 7 | PD35 | PD34 | PD33 | PD32 | PD31 | PD30 | PD23
2024-04-01 | [9 empty] | PD 19 | PD 12 | PD 11 | PD 8 | PD36 | PD35 | PD34 | PD33 | PD32 | PD31 | PD24
2024-04-02 | [9 empty] | PD 20 | PD 13 | PD 12 | PD 9 | PD37 | PD36 | PD35 | PD34 | PD33 | PD32 | PD25
2024-04-03 | [9 empty] | PD 21 | PD 14 | PD 13 | PD 10 | PD38 | PD37 | PD36 | PD35 | PD34 | PD33 | PD26
2024-04-04 | [9 empty] | PD 22 | PD 15 | PD 14 | PD 11 | PD39 | PD38 | PD37 | PD36 | PD35 | PD34 | PD27
2024-04-05 | [9 empty] | PD 23 | PD 16 | PD 15 | PD 12 | PD40 | PD39 | PD38 | PD37 | PD36 | PD35 | PD28 | PD23
2024-04-06 | [10 empty] | PD 17 | PD 16 | PD 13 | PD41 | PD40 | PD39 | PD38 | PD37 | PD36 | PD29 | PD24
2024-04-07 | [10 empty] | PD 18 | PD 17 | PD 14 | PD42 | PD41 | PD40 | PD39 | PD38 | PD37 | PD30 | PD25
2024-04-08 | [10 empty] | PD 19 | PD 18 | PD 15 | PD43 | PD42 | PD41 | PD40 | PD39 | PD38 | PD31 | PD26
2024-04-09 | [10 empty] | PD 20 | PD 19 | PD 16 | PD44 | PD43 | PD42 | PD41 | PD40 | PD39 | PD32 | PD27
2024-04-10 | [10 empty] | PD 21 | PD 20 | PD 17 | PD45 | PD44 | PD43 | PD42 | PD41 | PD40 | PD33 | PD28
2024-04-11 | [10 empty] | PD 22 | PD 21 | PD 18 | PD46 | PD45 | PD44 | PD43 | PD42 | PD41 | PD34 | PD29
2024-04-12 | [10 empty] | PD 23 | PD 22 | PD 19 | PD47 | PD46 | PD45 | PD44 | PD43 | PD42 | PD35 | PD30 | PD23
2024-04-13 | [11 empty] | PD 23 | PD 20 |  | PD47 | PD46 | PD45 | PD44 | PD43 | PD36 | PD31 | PD24 | PD23
2024-04-14 | [12 empty] | PD 21 |  |  | PD47 | PD46 | PD45 | PD44 | PD37 | PD32 | PD25 | PD24
2024-04-15 | [12 empty] | PD 22 |  |  |  | PD47 | PD46 | PD45 | PD38 | PD33 | PD26 | PD25
2024-04-16 | [12 empty] | PD 23 |  |  |  |  | PD47 | PD46 | PD39 | PD34 | PD27 | PD26 | PD23
2024-04-17 | [18 empty] | PD47 | PD40 | PD35 | PD28 | PD27 | PD24
2024-04-18 | [19 empty] | PD41 | PD36 | PD29 | PD28 | PD25
2024-04-19 | [19 empty] | PD42 | PD37 | PD30 | PD29 | PD26
2024-04-20 | [19 empty] | PD43 | PD38 | PD31 | PD30 | PD27
2024-04-21 | [19 empty] | PD44 | PD39 | PD32 | PD31 | PD28
2024-04-22 | [19 empty] | PD45 | PD40 | PD33 | PD32 | PD29
2024-04-23 | [19 empty] | PD46 | PD41 | PD34 | PD33 | PD30
2024-04-24 | [19 empty] | PD47 | PD42 | PD35 | PD34 | PD31
2024-04-25 | [20 empty] | PD43 | PD36 | PD35 | PD32
2024-04-26 | [20 empty] | PD44 | PD37 | PD36 | PD33
2024-04-27 | [20 empty] | PD45 | PD38 | PD37 | PD34
2024-04-28 | [20 empty] | PD46 | PD39 | PD38 | PD35
2024-04-29 | [20 empty] | PD47 | PD40 | PD39 | PD36
2024-04-30 | [21 empty] | PD41 | PD40 | PD37
2024-05-01 | [21 empty] | PD42 | PD41 | PD38
2024-05-02 | [21 empty] | PD43 | PD42 | PD39
2024-05-03 | [21 empty] | PD44 | PD43 | PD40
2024-05-04 | [21 empty] | PD45 | PD44 | PD41
2024-05-05 | [21 empty] | PD46 | PD45 | PD42
2024-05-06 | [21 empty] | PD47 | PD46 | PD43
2024-05-07 | [22 empty] | PD47 | PD44
2024-05-08 | [23 empty] | PD45
2024-05-09 | [23 empty] | PD46
2024-05-10 | [23 empty] | PD47

## Cage change schedule (hidden)
Cage changes/weight after birth
DAM ID | PD8 | Weight | PD15 | Weight | PD22 | Weight
B7 | 2024-03-04 |  | 2024-03-11 |  | 2024-03-18
B18
B19
B16 | 2024-03-05 |  | 2024-03-12 |  | 2024-03-19
B13
B15
B4
B17
B10
B12 | 2024-03-07 |  | 2024-03-14 |  | 2024-03-21
B2
B6
B14
B11
B8
B9 | 2024-03-08 |  | 2024-03-15 |  | 2024-03-22
B26
B3
B5
B28
Formulas:
PD22 = [PD15]+7

## Offspring weights (hidden)
Dam ID | Pup ID | Sex | Postnatal day 30 | Weight | Date
B13 | BP5 | Female |  |  | 2024-03-27 | Done
BP6
| BP7 | Male
BP8
B15 | BP13 | Female
BP14
| BP15 | Male
BP16
Dam ID | Pup ID | Sex | Postnatal day 37 | Weight | Date
B13 | BP5 | Female |  |  | 2024-04-03
BP6
| BP7 | Male |  |  |  | Done
BP8
B15 | BP13 | Female
BP14
| BP15 | Male
BP16
Dam ID | Pup ID | Sex | Postnatal day 44 | Weight | Date
B13 | BP5 | Female |  |  | 2024-04-10
BP6
| BP7 | Male
| BP8 |  |  |  |  | Done
B15 | BP13 | Female
BP14
| BP15 | Male
BP16
Dam ID | Pup ID | Sex | Postnatal day 30 | Weight | Date
B12 | BP85 | Female |  |  | 2024-03-29
| BP86 |  |  |  |  | Done
| BP87 | Male
BP88
B6 | BP21 | Female
BP22
| BP23 | Male
BP24
B8 | BP29 | Female
BP30
| BP31 | Male
BP32
B14 | BP37 | Female
BP38
| BP39 | Male
BP40
Dam ID | Pup ID | Sex | Postnatal day 37 | Weight | Date
B12 | BP85 | Female |  |  | 2024-04-05
| BP86 |  |  |  |  | Done
| BP87 | Male
BP88
B6 | BP21 | Female
BP22
| BP23 | Male
BP24
B8 | BP29 | Female
BP30
| BP31 | Male
BP32
B14 | BP37 | Female
BP38
| BP39 | Male
BP40
Dam ID | Pup ID | Sex | Postnatal day 44 | Weight | Date
B12 | BP85 | Female |  |  | 2024-04-12
BP86
| BP87 | Male
BP88
B6 | BP21 | Female
| BP22 |  |  |  |  | Done
| BP23 | Male
BP24
B8 | BP29 | Female
BP30
| BP31 | Male
BP32
B14 | BP37 | Female
BP38
| BP39 | Male
BP40
Dam ID | Pup ID | Sex | Postnatal day 30 | Weight | Date
B9 | BP45 | Female |  |  | 2024-03-30
BP46
| BP47 | Male |  |  |  | Done
BP48
B26 | BP53 | Female
BP54
| BP55 | Male
BP56
B3 | BP61 | Female
BP62
| BP63 | Male
BP64
B28 | BP69 | Female
BP70
| BP71 | Male
BP72
Dam ID | Pup ID | Sex | Postnatal day 37 | Weight | Date
B9 | BP45 | Female |  |  | 2024-04-06
BP46
| BP47 | Male |  |  |  | Done
BP48
B26 | BP53 | Female
BP54
| BP55 | Male
BP56
B3 | BP61 | Female
BP62
| BP63 | Male
BP64
B28 | BP69 | Female
BP70
| BP71 | Male
BP72
Dam ID | Pup ID | Sex | Postnatal day 44 | Weight | Date
B9 | BP45 | Female |  |  | 2024-04-13
BP46
| BP47 | Male
| BP48 |  |  |  |  | Done
B26 | BP53 | Female
BP54
| BP55 | Male
BP56
B3 | BP61 | Female
BP62
| BP63 | Male
BP64
B28 | BP69 | Female
BP70
| BP71 | Male
BP72
Dam ID | Pup ID | Sex | Postnatal day 23 | Weight | Date
B30 | BP77 | Female |  |  | 2024-03-31
| BP78 |  |  |  |  | Done
| BP79 | Male
BP80
B34 | BP93 | Female
BP94
| BP95 | Male
BP96
Dam ID | Pup ID | Sex | Postnatal day 37 | Weight | Date
B30 | BP77 | Female |  |  | 2024-04-07
BP78
| BP79 | Male |  |  |  | Done
BP80
B34 | BP93 | Female
BP94
| BP95 | Male
BP96
Dam ID | Pup ID | Sex | Postnatal day 37 | Weight | Date
B30 | BP77 | Female |  |  | 2024-04-14
BP78
| BP79 | Male
BP80
B34 | BP93 | Female
BP94
| BP95 | Male
BP96
Dam ID | Pup ID | Sex | Postnatal day 44 | Weight | Date
B30 | BP77 | Female |  |  | 2024-04-21 | ****
BP78
| BP79 | Male
BP80
B34 | BP93 | Female
BP94
| BP95 | Male
BP96

## Labelling (hidden)
Chambers | Date needed by: | Brain Jars + blood tubes | Date needed by: | Chambers and brain jars only need animal ID,
B33 | 2024-03-28 | BP81 | 2024-03-29 | 1.5ML tubes need the ID, and S1, S2, and P1, P2
B27 |  | BP82 |  | This is so there are two tubes for serum, and two for plasma
B20 |  | BP83
B1 | 2024-03-29 | BP84
B30 | 2024-03-31 | BP17
B34 | April 1st | BP18
B23 |  | BP19
BP49 | 2024-03-30 | BP20
BP50 |  | BP25
BP51 |  | BP26
BP52 |  | BP27
BP57 |  | BP28
BP59 |  | BP33
BP73 | 2024-04-07 | BP34
BP74 |  | BP35
BP75 |  | BP36
BP76 |  | BP41 | 2024-03-30
BP81 |  | BP42
BP82 |  | BP43
BP83 |  | BP44
BP84 |  | BP58
BP89 |  | BP60
BP91 |  | BP65
BP37 | 2024-04-15 | BP66
BP39 |  | BP67
BP45 | 2024-04-16 | BP68
BP47 |  | BP90 | 2024-04-07
BP61 |  | BP92
BP62 |  | BP5 | 2024-04-13
BP63 |  | BP6
BP64 |  | BP7
BP69 |  | BP8
BP70 |  | BP13
BP71 |  | BP14
BP72 |  | BP15
BP16
|  | BP21 | 2024-04-15
BP22
BP23
BP24
BP29
BP30
BP31
BP32
BP38
BP40
|  | BP46 | 2024-04-16
BP48
BP53
BP54
BP55
BP56
|  | BP77 | 2024-04-24
BP78
BP79
BP80
BP93
BP94
BP95
BP96